## Sheet1
Team:	8H			Unit:	Person-hours

Sprint	ID	User story	Priority	Estimated effort	Actual effort	Done?
NA	1	As a visitor, I want to be able to order hotels based on distance from a given point so I can find hotels close to where I'll be spending my time.	30	5	NA	No
NA	2	As a visitor, I want to view pictures of the hotel and rooms to see if the room meets my expectations.	20	13	NA	No
2	3	As a visitor, I want to be able to read what amenities are available in the room in order to determine if the room matches my needs.	10	5	NA	No
2	4	As a visitor, I want to be able to sort rooms by size, price, and amenities, so I am able to pick a room that suits my needs.	10	8	NA	No
NA	5	As a visitor, I want to see which hotels are pet friendly, because I have allergies.	40	2	NA	No
NA	6	As a visitor, I want to see when the checkout time for the hotel is, so I can plan when to leave the room.	20	2	NA	No
NA	7	As a hotel manager, I want to be able to post a hotel and configure how many rooms are available and their respective prices, so I can give potential customers information about my hotel.	10	13	NA	No
NA	8	As a hotel manager, I want to be able to charge travelers who have booked a room, so I can confirm the booking.	10	20	NA	No
NA	9	As a hotel manager, I want to get payment information from customers when they book a room, so I have the ability to charge for late cancellation.	20	20	NA	No
NA	10	As a hotel manager, I want to be able to respond to reviews and dispute false ones, since reviews are very important when travelers choose hotels.	30	20	NA	No
NA	11	As a trip planner, I want to have an interface to bundle together room offerings, so I can make bookings on the behalf of my customers.	30	20	NA	No
NA	12	As a tax inspector, I need access to the tax identification numbers of the hotels, to fulfill my legal responsibility to survey hotel service providers.	30	?	NA	No

		Note: We only estimated the user stories we did in 1A, so there is no story here marked for the first sprint since that will have to be devoted to just setting up the framework we need